## Tabelle1
Riskmanagement – BFFL
Nr. | Risk Name | Risk Description | Occurrence (1-10) | Impact (1-10) | Risk Factor (Occurence * Impact) | Risk Mitigation | Person in Charge of Tracking
1 | A lot Learning | Everything we do is new to us | 10 | 10 | 100 | Timemanagement | Fabi
2 | Bad Planning | Disordered approach, No guidance, No experience | 10 | 8 | 80 | Replan project yourself | Felix
3 | Not enough focus | Participation, work beyond the lecture | 8 | 10 | 80 | Frequent meetings | Basti
4 | Not enough time | Not enough time for impl. without loss of quality | 7 | 10 | 70 | Change scope early | Lars
5 | Low Motivation | Low motivation due to poor prospects | 7 | 7 | 49 | Better planning | Felix
6 | Technical problems | Implementation not feasible, too costly, ... | 4 | 7 | 28 | Find other way, change scope | Team
7 | Bad Tools | Tools for Planning, Development, Communication | 5 | 4 | 20 | Use other tools | Basti
8 | Staff shortage | Illnesses etc. | 2 | 4 | 8 | N/A | Team
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0